## Project plan
LeanControl — Project Plan Import
Fill one structured table. Phase rows become headings; Main Task, Task and Subtask rows become expandable items in LeanControl.
Project information — fill once before entering the plan
Project Code* | Project Name* | Project Type* | Project Size* | Portfolio | Main PM Person ID* | Start Date | Target End Date
YOUR-PROJECT | Your Project Name | New | Medium | Your Portfolio | DEMO-RRMS-PM | 2026-09-01 | 2026-12-31
Work plan — replace the colored example rows, then add more rows below
Level* | Task No.* | Parent No. | Task Title* | Task Owner(s) | Assignee Person IDs | Duration (days) | Start Date | Due Date | Status* | Progress % | Priority | Evidence required | WBS Code | Notes
Phase | 1 |  | Exploration |  |  |  | 2026-09-01 | 2026-09-02 | Done | 100 | Medium | FALSE | YOUR-PROJECT-01 | Phase heading
Main Task | 1.1 | 1 | Feasibility assessment | PM; BA | DEMO-RRMS-PM | 2 | 2026-09-01 | 2026-09-02 | Done | 100 | Medium | FALSE | YOUR-PROJECT-01 | Example main task
Task | 1.1.1 | 1.1 | Confirm scope and approach | BA | DEMO-RRMS-PM | 1 | 2026-09-01 | 2026-09-01 | Done | 100 | Low | FALSE | YOUR-PROJECT-01 | Example task
Phase | 2 |  | Requirements |  |  |  | 2026-09-03 | 2026-09-16 | InProgress | 50 | High | TRUE | YOUR-PROJECT-02 | Phase heading
Main Task | 2.1 | 2 | Realize specification | PM; BA | DEMO-RRMS-PM | 10 | 2026-09-03 | 2026-09-16 | InProgress | 50 | High | TRUE | YOUR-PROJECT-02 | Example main task
Task | 2.1.1 | 2.1 | Meeting #1 — workflow as-is | BA | DEMO-RRMS-PM | 1 | 2026-09-03 | 2026-09-03 | Done | 100 | Medium | FALSE | YOUR-PROJECT-02 | Example task
Subtask | 2.1.1.1 | 2.1.1 | Record actions and open points | BA | DEMO-RRMS-PM | 1 | 2026-09-03 | 2026-09-03 | Done | 100 | Low | FALSE | YOUR-PROJECT-02 | Example subtask
Phase | 3 |  | Develop / Design |  |  |  | 2026-09-17 | 2026-10-31 | NotStarted | 0 | High | TRUE | YOUR-PROJECT-03 | Phase heading
Main Task | 3.1 | 3 | Design and development | BA; DEV | DEMO-RRMS-PM | 30 | 2026-09-17 | 2026-10-31 | NotStarted | 0 | High | TRUE | YOUR-PROJECT-03 | Example main task
Phase | 4 |  | Testing |  |  |  | 2026-11-01 | 2026-11-15 | NotStarted | 0 | Medium | TRUE | YOUR-PROJECT-04 | Phase heading
Phase | 5 |  | Training |  |  |  | 2026-11-16 | 2026-11-20 | NotStarted | 0 | Medium | FALSE | YOUR-PROJECT-05 | Phase heading
Phase | 6 |  | Go Live & Support |  |  |  | 2026-11-21 | 2026-11-30 | NotStarted | 0 | High | TRUE | YOUR-PROJECT-06 | Phase heading

## How to fill
How to fill the hierarchical plan
The structure is easy to enter in Excel and will become an expandable hierarchy after import.
What to enter
Phase | A colored section heading such as Requirements or Testing. It does not need an owner.
Main Task | A large delivery group under a Phase. Parent No. must be the Phase Task No.
Task | A deliverable under a Main Task. Parent No. must be the Main Task No.
Subtask | A smaller action under a Task. Parent No. must be the Task No.
Task No. | Use a simple hierarchy: 1 → 1.1 → 1.1.1 → 1.1.1.1.
Person IDs | Use IDs already listed in LeanControl People Master. Separate multiple assignees with semicolons.
Important rules for future upload
1 | Phase rows must have Level = Phase and no Parent No.
2 | Every Main Task / Task / Subtask must have a Parent No. that exists above it.
3 | Status Done requires Progress = 100. Dates use YYYY-MM-DD.
4 | WBS Code groups the work items. Use one WBS Code for each Phase unless you need a further split.
5 | Yellow project information cells and green rows are examples. Replace them before upload.

## Validation lists
Validation lists
Drop-down values for the Project plan sheet. Review these values before the Import feature is implemented.
Level | Project type | Project size | Status | Priority | True / False
Phase | New | Small | NotStarted | Low | TRUE
Main Task | Change Major | Medium | InProgress | Medium | FALSE
Task | Change Minor | Large | Blocked | High
Subtask | Job |  | Done
Cancelled